## Minutable
| ANALYSIS | PLANNING/ ADVICES | SOFTWARE TOOLS | TEST PROCEDURES | TEST SETUP | HIL AUTOM. | TEST EXECUTION | ISSUES TRACKING | MANAGEMENT | Input & Output Link
P702 | 04/15/20: ADAS flashed, stoped ADAS part borrowed 06/02/20: GIM-17410 bug when software update by USB- Implementation post job one +90 days, issue deferred, under revision; will provide OTA last implementation; fix by 12/21 |  |  |  | 09/20/20: Production part for LVDS for 11/16, TCU for 01/08 |  |  | 127 open tickets 40 issues availables to test |  |  | 09/18/19:SW briefcase TCU, ECG y SYNC on 10/14 10/09/19: IPC FEC software will not be compatible with current hardware. INFO
CX727 | [6 empty] | 04/15/20: ADAS flashed, stoped ADAS part borrowed | 67 open tickets 27 issues ready to test |  |  | 01/08/20: BLEM parts arrive. Test in 5th round.
U725 | [6 empty] | 06/17/20: Sync retest sync low testing, pending mid high | 65 open tickets 30 issues ready to test |  |  | *02/21/19: Hybrid version out of scope. INFO. *05/16/19: Informa que agosto es el due date para meter las RPS. INFO *10/16/19: Is informed ICP setup will be required until 2nd round. INFO.
U540 | 09/09/20: APA is not working properly, text is not displayed, IVI-19325, new information provided, validating information. 10/01/20: Load Sheid 18 issues; 10 Retest to update Evidence, 8 Tickets tester is going to reviewed Tickets. 10/20/20: 3 IPC Tickets following meeting 11/11, sources & phone menu does not work. | [6 empty] | 105 open tickets 21 ready to test |  | 008 FNV2 VR navigation TC pending, coexistance TCx pending hotspot. | 16/16/19: No DT files available for this program in SW briefcase, due 30-Nov. Achieved 10/21
CD539 | 09/09/20: Waiting Feedback Sync D&R 4 tickets; 3 Tickets Closed, 1 Pending Fix (IVI-16718). 10/01/20: Load Sheid 18 issues; 10 Retest to update Evidence, 8 Tickets tester is going to reviewed Tickets. | [6 empty] | 95 open tickets 18 ready to test |  |  | 16/16/19: No DT files available for this program in SW briefcase, due 30-Nov. Achieved 10/22
P758 | 06/16/20: Keypad issue cannot change code in CTR, BCM ticket; Discussing between D&R responsibles; BCM & CTR, ISDV to test received CTR, new software drop received, test by 10/20, will be test on breadboard 11/10 07/27/20: Chimes 1 test pending, rear speakers apply to program; spec info mismatch, discussing, cluster /CTR passed in yellowboards, supplier retest passed, tested in bench to confirm issue 10/13, issue persist, follow up vehicle test testing/results under confirmation. 06/16/20: CTR Issues will be solved until SW fix release at October -PEC-, sw intermediate 10/27, official 11/02 week, delayed, confirming SW release drop, scalated by PMT. 06/17/20: Cluster Denso & CTR is not displaying media and phone menu; Following with core europe & PMT; Denso ST min by 10/30; technical confirmation, 11/10 feedback from supplier, D&R checking SW update. 09/23/20: Brightness Issue, could be solved by calibration, team to perform calibration check for issue closure | [6 empty] | 12 open ticket all under analysis |  |  | 05/16/19. Reporta riesgos para completar features, pedira soporte de writing in Europa. INFO. 11/13/19: HIL productive testing requests and SYNC SW version confirmation delayed delivered on 11/18.
P558 | [7 empty] | 17 tickets 2 ready to test, fixing box for retest
U553 | 07/13/20: Infotainment menues does not work, LX (Visteon) SW infotainment implementation until sprint 4.3, changed to sprint 4.5, official release 12/11 complete implementation until 01/27. SW 4.4 requires parts at visteon's 07/20/20: Infotainment menues does not work, L2 eng. drop testing, issue persist in official DCV3 SW following up, fix for 03/02/21 06/30/20: Database signals mismatch between D&R and FNV2 team; 23 FNV2 update is required for 3rd round 01M 21 07/21/20: Applink walkarounds needed to enable Navigation apps (Waze, Antilop, will be solved in production (MP1) 07/21/20: Sync Graphics Templates are not implemented. (welcome screen, frameworks & brand logos with defects, ticket need to update) implementation SW release by 11/30, FNV2.0.3.2 11/30 IVI 18673. |  |  |  |  | 11/04/20: Send request to analysis to confirm parts are available. Part enter CSAP 11/11, pending AHU & DSP. | 09/30/20: SCCM problem boot loader. Issue wih Key at configuration. | 11/04/20: RSEM 3 Issue, sent evidence, waiting feedback on JIRA |  |  | INFO 10/02/19: AHU to use surrogate parts. 09/25/19: Second DB Analysis Required November 8th (UPV2 +1 week).Completed 03/04/20: INFO. Team this are the new dates for this program: FDJ 01/31; DCV0 05/08; DCV1 06/19; DCV2 07/13.
U554 | 07/13/20: Infotainment menues does not work, LX (Visteon) SW infotainment implementation until sprint 4.3, changed to sprint 4.5, official release 12/11, complete implementation until 01/27.SW 4.4 required parts at Visteon's 06/30/20: Database signals mismatch between D&R and FNV2 team; 34 FNV2 signals require update, update required for 3rd round 01M 21, following up meeting 11/12 08/19/20: Climate feature is not displaying climate bar buttons, IVI 18822; tentative implementation 11/30 08/10/20: Audio Lincoln Features (Revel Demos, Inmersion Modes, etc) are not implemented on Sync, IVI-17999; following up fix release SYNC group by 11/30 09/20/20: IVI-19166, it shows sound mode when DSP rebel is present, next official FNV2.0.3.1 until 11/30, will be tested with an intermediate (master) SW 07/21/20: Applink walkarounds needed to enable Navigation apps (Waze, Antilop); tested on FNV2-2020-08M, passed in Build 1440, walks around are needed at dev. level IVI-18547 until TT 07/21/20: Sync Graphics Templates are not implemented, IVI-18672 (welcome screen, frameworks & brand logos with defects), fix until 11/30, FNV2.0.3.2 09/02/20: Dueros is waiting Software Update Tool; tools provision, declared is sent, need supplier info & then Ford payment, following up: approver payment |  |  |  |  | 11/04/20:Info: Is confirm that SYNC ghrapics nativs U540 | 08/19/20: 2 IPC LX for reflash, waiting to return to CSAP 10/14/20: Stolen vehicle is not working, checking with feature owner. 11/04/20: SCCM configuration problem, checking additional SCCM and different harness. 11/11/20: Vehicle health features is blocked. |  |  |  | 09/25/19: Second DB Analysis Required November 8th (UPV2 +1 week). Completed. 03/18/20: Writting is responsible of attributes settings.
P702 BEV | 09/02/20: 63 FNV2 Signals signals that required an update, update is requried for 01M 21 06/10/19: Functional Safety & Vehicle Inhibit. Issue blocker, P702 - SYNC-154127, SYNC-154535, SYNC-151810 & SYNC-152265. CX727 - SYNC-142915, SYNC-154128 & SYNC-154129, Fixes are expected on 30/Nov/20. FNV2-2020-11M. | 11/11/20: Need meeting request for PMT meeting |  | 10/14/20: Frunk Softswitch v2, eLocker Soft Switch, Clear Exit Assist (SYNC-136393), Trailer Settings v1.3, Remote Park Assist (RePA), Selectable Drive Mode Testing debug is missing, pending arrive parts 10/14/20: Display Mode (Day Night Mode), Audio Settings v1.5, Multi-Camera Client APIM v1.12-1.13 Trailer Settings v1.1-1.2, Due 10/19: Power Management Update for versions 1.12-1.13, Rear View Camera Client (Standalone) v2.8 due 11/13. 10/14/20: Trailer Backup Assist 2.0 Image Client APIM SPSS (v1.5-v1.6), Onboard Scale - 15" Dashcard HMI, Smart Hitch v1.2, | 07/22/20: BLEM part request for 07/22 delayed, request updated, new promise date 11/26. |  | 10/14/20: Trailer settings are not correct, checking TCs with writing team and FO. 13/10/2020: Diana's bench problem with Ford Pass authorizacion. EV trip planner, cannot provisioning 11/04/20:OBCC request to update part2 for plug in charge, cannot provisining. 11/04/20: ADAS is needed for multicamera, will continue test
P703 | 05/20/20: HIL SW Sync confirmation is FNV2-2021-01M 07/22/20: Due 01/08/21 Topology ECU markets mismatch. Blem ECU & features Lincoln Backup Ignition and Phone as a Key. Pending CFR conclusion, to be concluded by FDJ; backup strategy is to use BLEM gen 1& 2 requested in other programs. 10/28/20: Problems with IPC software, Supplier provide info about how to flash, pending approval for digital storage, following. | 11/04/20: First round FDJ 01/08/21. 11/11/20: Need meeting request for PMT meeting |  | 06/10/20: Off-Road Controls, updating, HMI new version. 06/10/20: Bezel Diagnostics v1.8, Button Strategy (Network Based) v1.6 due 01/08/21, Planned to start end November | 0 0 0 6
CX482 | 08/25/20: Sync 4.0 Pending definition of complexity Matrix; GPIRS purchacing procces (costs & supplier codes) to close end 11M/20 purchasing by 12/20, back up plan to request parts to HW design engineer, possible part deliver by 02M 2021. 11/11/20: INFORMATIVE Sync ,EGC & TCU pinout changes due to more buses | Possible delay from FDJ due to SYNC 11/11/20: Need meeting request for PMT meeting |  |  | 10/28/20: Parts with RPS 18 dic
CX483 | 10/20/20: Sync 4.0 Pending definition of complexity Matrix; GPIRS purchacing procces (costs & supplier codes) to close end 11M/20 purchasing by 12/20, back up plan to request parts to HW design engineer, possible part deliver by 02M 2021. 11/11/20: IPC SOBA not defined, high risk part at FDJ unavailable 11/11/20: INFORMATIVE Sync ,EGC & TCU pinout changes due to more buses | Possible delay from FDJ due to SYNC 11/11/20: Need meeting request for PMT meeting |  |  | 10/28/20: Parts with RPS
P708 | 10/20/20: UIM Pending to define Possible Change, request to test procedures for feedback, meeting with D&R by 11/17. 10/20/20: TCU Pending Supplier code and Cost. by 12/07 10/20/20: ECG Pending Supplier Code and Cost. checking compatibilty with CX48X, posible to use same part. 11/04/20: Pending to confirm SYNC part number, D&R does not answer. 11/11/20: INFORMATIVE Sync ,EGC & TCU pinout changes due to more buses |  |  | Mobile Device Viewer Analyze feature (UIM) to check possible requirements for testing, to have result by 11/11.
S650 | 10/28/20: Waiting; final topology version by 11/20, for planning testing closure 10/28/20: Sync 4A Part numbers are not defined. following up 10/28/20: TCU G2 Pending Supplier code and Cost; until December 10/28/20: IPC SX confirm Supplier code and Cost. following up 11/11/20: INFORMATIVE Sync ,EGC & TCU pinout changes due to more buses | 11/11/20: Need meeting request for PMT meeting

## Sheet1
P702 MY21 | Round 1 | 001 | Round 2 | 006 | Round 3 | 009 | Round 4 | 013 | Round 5 | 017 |  |  | Round 6 | 019 | 2020-02-11 | 2020-05-05 | Round 7 | 022 | 2020-05-19 | 2020-07-10
|  | 002 |  | 007 |  | 010 |  | 014 |  | 018 |  |  |  | 020 | 2020-02-11 | 2020-05-06 |  | 023 | 2020-05-19 | 2020-07-14
|  | 004 |  | 008 |  | 011 |  | 015 | [5 empty] | 021 | 2020-02-11 | 2020-05-01 |  | 024 | 2020-05-19 | 2020-07-14
|  | 005 |  |  |  | 012 |  | 016
CX727 MY21 | Round 1 | 002 | Round 2 | 007 | Round 3 | 009 | Round 4 | 013 | Round 5 | 015 | 2020-02-11 | 2020-05-06 |  |  |  |  | Round 6 | 016 | 2020-05-19 | 2020-08-14
|  | 003 |  | 008 |  | 010 |  | 014
|  | 004 |  |  |  | 011
012
U725 MY21 | Round 1 | 002 FDJ |  |  | Round 2 | 005 DCV2 | 2020-01-08
|  | 004 FDJ |  |  |  | 006 DCV2
|  | 001 DCV0 |  |  |  | 007 DCV2
|  | 003 DCV0 |  |  |  | 008 DCV2 |  | 2020-02-26
U540 MY21 | Round 1 | 001 | 2020-01-06 | 2020-02-05 | Round 2 | 004 | 2020-04-29 | 2020-05-13 | Round 3 | 007 | [6 empty] | Round 3 | 007 | 2020-07-29 | 2020-08-11
|  | 002 | 2020-01-06 | 2020-02-04 |  | 005 | 2020-04-21 | 2020-05-13 |  | 008 | [7 empty] | 008 | 2020-07-06 | 2020-08-20
|  | 003 | 2020-01-06 | 2020-02-26 |  | 006 | 2020-04-27 | 2020-07-03 |  | 009 | [7 empty] | 009 | 2020-07-28 | 2020-08-06
CD539 MY21 | Round 1 | 001 |  |  | Round 2 | 004 | 2020-05-12 | 2020-06-08 | Round 3 | 007 | [6 empty] | Round 3 | 007 | 2020-07-28 | 2020-08-10
|  | 002 | 2020-01-06 | 2020-02-07 |  | 005 | 2020-04-30 | 2020-05-22 |  | 008 | [7 empty] | 008 | 2020-07-06 | 2020-08-17
|  | 003 | 2020-02-18 | 2020-03-09 |  | 006 | 2020-04-27 | 2020-06-26
P758 MY22 | Round 1 | 001 | 2020-01-02 | 2020-02-13 | [12 empty] | Round 1 | 001 | 2020-01-02 | 2020-02-13
|  | 002 | 2020-05-22 | 2020-06-22 | [13 empty] | 002 | 2020-06-10 | 2020-06-25
|  | 003 | 2020-02-18 | 2020-03-09 | [13 empty] | 003 | 2020-02-17 | 2020-03-20
P558 MY22 | Round 1 | 006 | 2020-04-27 08:00 | 2020-05-13 17:00 | [12 empty] | Round 1 | 006 | 2020-04-23 | 2020-06-15
|  | 007 | 2020-05-14 08:00 | 2020-06-24 17:00 | [13 empty] | 007 | 2020-06-16 | 2020-07-07
|  | 008 | 2020-06-25 08:00 | 2020-08-19 17:00 | [13 empty] | 008 | 2020-07-08 | 2020-08-28
U553 MY22 | Round 1 | 001 | 2020-03-11 | 2020-05-01 | Round 2 | 004 | 2020-07-27 | 2020-09-04 | [8 empty] | Round 1 | 001 | 2020-03-11 | 2020-07-31
|  | 002 | 2020-03-10 | 2020-05-08 |  | 005 | 2020-07-27 | 2020-09-04 | [9 empty] | 002 | 2020-03-10 | 2020-07-27
|  | 003 | 2020-05-11 | 2020-07-24 |  | 006 | 2020-07-27 | 2020-09-04 | [9 empty] | 003 | 2020-05-11 | 2020-08-04
U554 MY22 | Round 1 | 001 | 2020-03-12 | 2020-05-06 | Round 2 | 004 | 2020-07-27 | 2020-09-04 | [8 empty] | Round 1 | 001 | 2020-03-12 | 2020-05-18
|  | 002 | 2020-06-23 | 2020-08-10 |  | 005 | 2020-07-27 | 2020-09-04 | [9 empty] | 002 | 2001-09-01 | 2020-10-02
|  | 003 | 2020-03-13 | 2020-06-04 |  | 006 | 2020-07-27 | 2020-09-04 | [9 empty] | 003 | 2020-03-13 | 2020-07-03
rou
P703 MY22
P702 BEV MY22
Note on G16: De la cruz, Enrique (E.): del 17 de Febreo al 11 de Mayo. Del 6 de abril al 05 de junio.
Note on K16: De la cruz, Enrique (E.): del 17 de Febreo al 11 de Mayo. Del 6 de abril al 05 de junio.
Note on S16: De la cruz, Enrique (E.): del 17 de Febreo al 11 de Mayo. Del 6 de abril al 05 de junio.
Note on G20: De la cruz, Enrique (E.): Checar que ya esté contemplada la segunda ronda.
Note on K20: De la cruz, Enrique (E.): del 17 de Febreo al 11 de Mayo. Del 6 de abril al 05 de junio.
Note on S20: De la cruz, Enrique (E.): del 17 de Febreo al 11 de Mayo. Del 6 de abril al 05 de junio.

## rounds
| START | END
First | FDJ | DCV0
Second | DCV2 | DCV3
Third | DCV3 | PEC (R00)
Fourth | PEC (R00) | FEC (R04)
Fifth | FEC (R04) | TT (R05)
Sixth | TT (R05) | PP (R06)
Seventh | PP(R06) | MP1 (R07)
|  |  |  | Weekly Reported | Proposed | Final
|  |  | P702 Round 7. | July 14th | MP1 September 21st | MP1 September 21st
|  |  | CX727 Round 6 | August 14th | MP1 September 04th | MP1 September 04th
|  |  | U540 Round 3 | August 20th | TT September 14th | TT September 18th
|  |  | CD539 Round 3 | August 17th | TT September 14th | TT September 18th
|  |  | P558 Round 1 | August 28th | PEC September 11st | PEC + 19 September 30th | 12 de octubre
|  |  | U553 Round 2 |  | august 28th | October 23th---> 16 Nov.
|  |  | U554 Round 2 |  | august 28th | October 23th ---> 16 Nov.
|  |  | P703 Pre FDJ |  |  | October 09th